## _ChartData
PROGRESS BY SECTION
Section | Completed | In Progress | Pending
Transformer Bay | 0 | 0 | 10
Switchgear | 0 | 0 | 10
Protection | 0 | 0 | 10
Cables | 0 | 0 | 10
Substation | 0 | 0 | 10
Panel Board | 0 | 0 | 10
Custom | 0 | 0 | 10
OVERALL | 0 | 0 | 70
COMMISSIONING TIMELINE
Equipment | Start Offset | Duration (days)
Transformer | 0 | 16
CT - Protection | 2 | 5
CT - Metering | 4 | 4
VT | 5 | 3
Circuit Breaker | 6 | 6
Relay - MiCOM P139 | 8 | 6
PQM | 10 | 3
CUBICLE | 11 | 5
NER | 13 | 4
Energization | 16 | 4
Cable Tests | 18 | 5
Substation Checks | 20 | 3
Integration | 22 | 5